## Status Report Page 1
Senior Design Status Report (Page 1) | [9 empty] | List Data - Do Not Edit
| Project Name: | Music Matters Booking System | [7 empty] | Completed | 1
| Team Members: | Chase Dumbacher, Sarah Pham, Austin Mongold, Austin Newkirk | [7 empty] | Discarded | 2
| Date: | 2021-03-11 | Cycle: | 2 | [5 empty] | Collaboration | 3
Adversarial
| System Metaphor: | To design and create an app and online calendar booking system that is capable of recording and organizing artist names, performance time and dates, and venue names as well as automatically creating and emailing invoices and confirmation documents. | [7 empty] | In Review
Unstarted
| Cycle Intent: | Begin bug fixing the iOS app and allowing Mike to begin testing it as well as setting up the main pages of the website and getting it to a demo-able point
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Database To App/Web Sync |  | 2 | 5 | 0 | Completed | 0 | 3
2 | Create Website Framework |  | 1 | 10 | 0 | Completed | 0 | 6
3 | Website Login With FireBase Auth |  | 1 | 3 | 0 | Completed | 0 | 3
4 | Allow Full Cross Platform Usage |  | 3 | 20 | 10 | Collaboration | 1 | 2
5 | Easy To View Calendar |  | 2 | 10 | 10 | Collaboration | 11 | 12
6 | Database Security |  | 3 | 8 | 0 | Collaboration | 0 | 2
7 | App Update And Recovery |  | 3 | 5 | 0 | Collaboration | 0 | 2
8 | Clean User Interface |  | 2 | 15 | 5 | Collaboration | 1 | 1 | Will likely be ongoing
9 | Football Event Scrapper (Web and iOS) |  | 3 | 30 | 10 | Collaboration | 0
11 | Functional Web Pdf Builder + Emailer |  | 2 | 30 | 10 | Unstarted | 0
12 | Functional App Pdf Builder + Emailer |  | 1 | 15 | 10 | Collaboration | 13 | 32
13 | Bug Fix iOS App |  | 2 | 40 | 10 | Collaboration | 2 | 24
14 | Refactoring iOS App |  | 2 | 20 | 5 | Collaboration | 0 | 11
Planned Total |  |  |  | 211 | 70 | Actual Total | 28 | 98

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Music Matters Booking System Team 5
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Chase Dumbacher | 1-4,6,7, 12-14 | 1, 6,7, 12-14 | 1, 6,7, 12-14 | 1-4, 6,7,12-14 | 25 | 0 | 0 | 1 | 1 | 0 | 0 | 7.5 | 7.5 | 8.5 | 8.5
| Sarah Pham | 6,7, 12-14 | 6,7, 12-14 | 6,7, 12-14 | 6,7,12-14 | 25 | 0 | 0 | 1 | 1 | 1 | 1 | 8 | 8 | 10 | 10
| Austin Mongold |  | 5 | 5 |  | 20 | 0 | 0 | 1 | 3 | 0.75 | 1.5 | 6 | 13 | 7.75 | 17.5
| Austin Newkirk | 2, 3, 5, | 2, 3, 5, | 2, 3, 5, | 2, 3, 5, | 20 | 0 | 0 | 2 | 3 | 1 | 2 | 3 | 12 | 6 | 17
[5 empty] | Totals | 90 | 0 | 0 | 5 | 8 | 2.75 | 4.5 | 24.5 | 40.5 | 32.25 | 53
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| App Acomplishments : - Successfullly got emailer working with all documentation except calendar export - Successfully changed sender of the emailer to MusicMatters email and setup app password for it - Setup secondary Dev enviornment for working on the app when schedules conflict. Web Acomplishments : - Figured out how to use a loop to create an event array - Figured out how to import google calendars from online | [6 empty] | App Objectives: - Work on Football scrapper and test it - Test and let Mike do end-end testing on documentation generater/emailer - Make adjustment to any email formats according to Mikes feedback. - Confirm and test document send out by specific date. Web Objectives: - Finish up calendar firebase data display - Start working on data insterter for calendar - Figure out why sports calendar imports aren't working
| Obstacles encountered since last status report: | [6 empty] | Notes:
| App Team: - - Web Team: - Javascript is still executing code out of order, and the things we've tried haven't worked yet - For some reason the sports calendars from google calendars won't work, but all the other calendars we have tested work | [6 empty] | - Mike is currently satisfied with current pacing of the project and seems to think we are moving faster/better then preivous groups - Task mangement and tracking has been moved to Monday.com it creates gantt charts based on board tasks and thus helps provide a mangement plan. - The plan should be viewable here https://view.monday.com/1068854366-9fbc2a1db7bba73d7f3618c436ab6452?r=use1 - Team has split into two pairs to help more efficentely work on the two sides of the project (App and Web Teams). Currently the app team is pair programming in effort to better review and bugfix the iOS app. Web team is using a mix of pair programming and scrum like task divying work flow.
Risks facing the project:
App Risk : - Web Risk : - Javascript executing out of order might cause issues in the future, and may require a rework of the firebase data search code

## Chase D.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Chase Dumbacher
Week Ending: |  | 2021-03-12
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Monday | Task(s) performed: | Worked on emailer and document generation functions for the app. Created test cloud function and tested indivual parts of documentation generation and emailing to determine specific location of error. Also worked on correcting and updating user stories for the status report
Date: | 2021-03-08 | Result: | Successfully got the artist confirmation documents generating and being sent from developer test email.
Hours Worked: | 2.5 | Problems encountered: | Still getting internal errors when working with invoice doucment generation and emailer. Currently a possible cause is being looked into
Day: | Tuesday | Task(s) performed: | Setup working enviornment on a personal Mac to allow me and Sarah to work seperate when time conflicts arise. Further worked on emailer. Worked on getting the emails sent through NodeMailer to be sent by Mike's email. This required working around googles lack of authorization for third-party applications. Also worked on narrowing down issues in invoice send out function.
Date: | 2021-03-09 | Result: | Successfully setup third-party acess to Mikes email from NodeMailer. Also succesfully setup working enviornment on barrowed personal mac. Progress was made on what parts of the invoice send out are failing, but specifics still being worked on.
Hours Worked: | 2 | Problems encountered: | Invoice send out still has errors that are deeper then the surface level function calls. This differes from the Confimration send out.
Day: | Wenesday | Task(s) performed: | Further worked on the documentation functions. confirmed the functionalitiy of timed sent out of documents. Also fixed the issues in the invoice confirmation, booking list, and began looking into the calendar export.
Date: | 2021-03-10 | Result: | All documentation functions ands related email functions are fully working as far as has been tested, with the exception of the calendar export which is being looked into
Hours Worked: | 2 | Problems encountered: | pdf.generators where referencing non-existent data objects that caused errors in generation and consquentially the documentation invoice functions. Currently the calendar export is reciving a similar error to past functions, however the cause is still unknown
Day: | Thursday | Task(s) performed: | Continued working on calendar export functionality and assured the test ready-ness of the documentation functions to present and to Mike for user end-to-end testing
Date: | 2021-03-11 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Planned work on confirming and testing documentation functions as well as the football scarpper.
Date: | 2021-02-12 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2021-02-10 | Result:
Hours Worked: |  | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2021-02-11 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2021-02-12 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2021-02-15 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2021-02-16 | Result:
Hours Worked: |  | Problems encountered:
Total Hours For The Week |  |  |  | 8.5

## Sarah P.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Sarah Pham
Week Ending: |  | 2021-03-12
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Monday | Task(s) performed: | Worked on emailer and documentation. Generated cloud functions for the app and tested them. Researched and gained exponential knowledge on Google Firebase and how Cloud Functions uses "containers" similar to Docker Containers. We were able to test certain portions of the code that were not able to be tested through "node [File name]" because of the containerization. Through testing different methods and functions that were very deep in the code, we were able to identify any bugs and runtime errors.
Date: | 2021-03-08 | Result: | Emailing system works with Gmail!
Hours Worked: | 2 | Problems encountered: | Getting issues from other features that are similar to "Artist Confirmations", such as the Artist Invoice, Booking List, and Calendar send out. However, since we were able to identify the issue with Artist confirmation and successfully come up with a solution, these other features should not be too difficult. Especially now that we have a greater understanding of the code, specifically javascript and react-native
Day: | Tuesday | Task(s) performed: | Worked on writing up documentation on each error and the corresponding resolution. Found more simulator related bugs. Redeployed Cloud functions and gained a deeper and comprehensive knowledge of containerization. Refactorization of code. Researching of javascript, firebase tools, and expo. Gaining further knowledge of how our project is able to create a pdf and export/send it.
Date: | 2021-03-09 | Result: | A more well-rounded documentation and deeper knowledge of Firebase-admin, Firebase-functions, devDependencies, node_modules, and partitioning of index.js
Hours Worked: | 2 | Problems encountered: | Features listed from Monday are still broken, however we are two steps closer to figuring them out!
Day: | Wenesday | Task(s) performed: | Worked on the Artist Invoice and Booking List, and after many hours of testing and redeploying/recontainerizing functions, and analyzing the realtime database, we successfully got it to work! Also worked on lots of documentation for our successes, our thought process, where we started, how much we plan to accomplish, and the solution to each bug/error we run into. Also handling our Git repo for the project in terms of merging pull requests, creating branches from a working branch and working from a locally saved Git.
Date: | 2021-03-10 | Result: | In Generate Forms feature => Artist Confirmations, Artists Invoice, and Monthly Booking List are all successfully working. The only thing left is sending out the entire Calendar and emailing/sending to the drive (currently does not work). We have a nicely generated code documentation that is being handled everyday.
Hours Worked: | 2 | Problems encountered: | The invoice was trying to pull data that did not exist in the database and that caused much confusion since the generation of the invoice and confirmation pdf's were extremely similar (about 100 lines of duplicated code). The confirmation pdf's were working for us and the invoice ones were not, in which you can see the confusion.
Day: | Thursday | Task(s) performed: | Working on the Calendar feature and fixing and bugs before uploading a new testflight for Mike before the meeting on Friday. He is quite responsive and downloads every testflight without being asked. Worked on the Status Report Cycle 2 Week 1.
Date: | 2021-03-11 | Result: | A new version of the app available on testflight with the working functionalities of the major emailing system. A completed status report for our class.
Hours Worked: | 2 | Problems encountered: | Whenever you try to export/send a "Monthly Calendar", we receive an internal error that does not really give us much information. Nothing is received on the email end, and all logs from the firebase cloud functions point to user code error.
Day: | Friday | Task(s) performed: | Meeting with Mike and working on small UI bugs and anything looking into the "Export to Excel" feature.
Date: | 2021-03-12 | Result: | A happy Mike.
Hours Worked: | 2 | Problems encountered: | Hopefully no problems.
Total Hours For The Week 10

## Austin M.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Mongold
Week Ending: |  | 2021-03-12
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2021-02-15 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2021-02-16 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on calendar-firebase code and worked on calendar import code, worked on cycle 2 week 1 report
Date: | 2021-02-17 | Result: | Made a lot of progress, and I think all that is left is figuring out how to tackle the async code execution
Hours Worked: | 7 | Problems encountered: | Code executing out of order or not saving variable data, sports calendars failing to import, but all other kinds are working
Day: | Thursday | Task(s) performed:
Date: | 2021-02-18 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2021-02-19 | Result:
Hours Worked: |  | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2021-02-20 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2021-02-21 | Result:
Hours Worked: |  | Problems encountered:

## Austin N.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Newkirk
Week Ending: |  | 2021-03-12
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Saturday | Task(s) performed: | UI changes to calendar (requested by Mr. Moody)
Date: | 2021-03-06 | Result: | Changes that makes the calendar similar to what Mr. Moody is used to.
Hours Worked: | 2 | Problems encountered: | The exact format in how Mr. Moody wants the calendar might not be possible, specifically how the time works. WIll look into more, in the future.
Day: | Sunday | Task(s) performed: | Looked into combining multible calendar sources (like holidays, football games, and firebase data) into one calendar
Date: | 2021-03-07 | Result: | Little change
Hours Worked: | 1 | Problems encountered: | Ran into an issue where all the data would disappear from the calendar except from 1 sources. Later figured out how to fix (kinda)
Day: | Tuesday | Task(s) performed: |  |  | Note: Had some personal issues come up during this day. I had an exam, and recieved a call that my grandmother was in the hospital from a stroke. Had to make an exmergency trip to Huntsville. I have my laptop to work, but work hours went down as a result of the incident. Turns out my grandma had a TIA, which isn't good, but a lot better news than excepted. She's good now :)
Date: | 2021-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Caught up with the teams work, currently trying to diagnose bugs with the displaying of data on the website (the same one from the presentation), and displaying the firebase data on the website
Date: | 2021-03-11 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Plan on figuring out how to display all the information we need on the calendar (football games and firebase data)
Date: | 2021-03-12 | Result: | Hopefully complete whats planned
Hours Worked: | Planned 2-3 | Problems encountered:
Day: | Friday | Task(s) performed: | Meeting with Mike
Date: | 2021-03-12 | Result:
Hours Worked: | Planned 1 | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
| Total Hours For The Week | 5 |  | Possible 7-8