## Status Report Page 1
Senior Design Status Report (Page 1) | [9 empty] | List Data - Do Not Edit
| Project Name: | Music Matters Booking System | [7 empty] | Completed | 1
| Team Members: | Chase Dumbacher, Sarah Pham, Austin Mongold, Austin Newkirk | [7 empty] | Discarded | 2
| Date: | 2021-03-11 | Cycle: | 2 | [5 empty] | Collaboration | 3
Adversarial
| System Metaphor: | To design and create an app and online calendar booking system that is capable of recording and organizing artist names, performance time and dates, and venue names as well as automatically creating and emailing invoices and confirmation documents. | [7 empty] | In Review
Unstarted
| Cycle Intent: | Finishing up all documentation functions and assure they are can be properly emailed from the iOS app as well as finishing the website calendar and assuring it meets Mike standards. The Web team is also planned to begin looking into web side pdf builders and possibity of using containerized firebase functions from iOS Team
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Database To App/Web Sync |  | 2 | 5 | 0 | Completed | 0 | 3
2 | Create Website Framework |  | 1 | 10 | 0 | Completed | 0 | 6
3 | Website Login With FireBase Auth |  | 1 | 3 | 0 | Completed | 0 | 3
4 | Allow Full Cross Platform Usage |  | 3 | 20 | 10 | Collaboration | 1 | 2 | Added a bit of functionality web-side that added to this
5 | Easy To View Calendar |  | 2 | 10 | 10 | Collaboration | 5 | 18
6 | Database Security |  | 3 | 8 | 0 | Collaboration | 0 | 2
7 | App Update And Recovery |  | 3 | 5 | 0 | Collaboration | 0 | 2
8 | Clean User Interface |  | 2 | 15 | 5 | Collaboration | 1 | 1 | Will likely be ongoing
9 | Football Event Scrapper (Web and iOS) |  | 3 | 30 | 10 | Collaboration | 0
11 | Functional Web Pdf Builder + Emailer |  | 2 | 30 | 10 | Unstarted | 0
12 | Functional App Pdf Builder + Emailer |  | 1 | 15 | 10 | Collaboration | 21 | 40
13 | Bug Fix iOS App |  | 2 | 40 | 10 | Collaboration | 3 | 25
14 | Refactoring iOS App |  | 2 | 20 | 5 | Collaboration | 0 | 11
Planned Total |  |  |  | 211 | 70 | Actual Total | 31 | 113

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Music Matters Booking System Team 5
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Chase Dumbacher | 1-4,6,7, 12-14 | 1, 6,7, 12-14 | 1, 6,7, 12-14 | 1-4, 6,7,12-14 | 25 | 0 | 0 | 0.5 | 1.5 | 0.5 | 0.5 | 5 | 12.5 | 6 | 14.5
| Sarah Pham | 6,7, 12-14 | 6,7, 12-14 | 6,7, 12-14 | 6,7,12-14 | 25 |  | 0 | 0.5 | 1.5 | 0.5 | 1 | 5.5 | 11.5 | 6.5 | 14
| Austin Mongold |  | 5 | 5 |  | 20 | 0 | 0 | 0.5 | 3.5 | 0.5 | 1 | 5 | 18 | 6 | 22.5
| Austin Newkirk |  | 5 | 5 | 5 | 20 | 0 | 0 | 0.5 | 3.5 | 0 | 2 | 2 | 12 | 2.5 | 17.5
[5 empty] | Totals | 90 | 0 | 0 | 2 | 10 | 1.5 | 4.5 | 17.5 | 54 | 21 | 68.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| App Acomplishments : - Successfully got new TestFlights deployed for Mikes testing - Successfully got calendar exporter and emailer working - Found new navigation bugs and began fixing - Setup console logs in the code to better understand where errors are happening in problematic functions Web Acomplishments : - Figured out football calendar issues - | [6 empty] | App Objectives: - Work on Football scrapper and test it - Listen to Mikes feedback and look for any possible changes on app as a whole - Fix navigation bug concerning to venue edit - Test large numbers of bookings/full calendars Web Objectives: - Get web calendar to a functional state - -
| Obstacles encountered since last status report: | [6 empty] | Notes:
| App Team: - Dependency updates seem to have effected page navigation and require fixing. - Discussion with Mike needs to be had about 'Excel Export' button and whether it is needed Web Team: - Javascript is still executing code out of order, and the things we've tried haven't worked yet - For some reason the sports calendars from google calendars won't work, but all the other calendars we have tested work Web Team: - Still the same obstacles as last time with code executing out of order | [6 empty] | - Mike is currently satisfied with current pacing of the project and seems to think we are moving faster/better then preivous groups - Task mangement and tracking has been moved to Monday.com it creates gantt charts based on board tasks and thus helps provide a mangement plan. - The plan should be viewable here https://view.monday.com/1068854366-9fbc2a1db7bba73d7f3618c436ab6452?r=use1 - Team has split into two pairs to help more efficentely work on the two sides of the project (App and Web Teams). Currently the app team is pair programming in effort to better review and bugfix the iOS app. Web team is using a mix of pair programming and scrum like task divying work flow.
Risks facing the project:
App Risk : - No current risk with the App progress has been fairly smooth. Web Risk : - Javascript executing out of order might cause issues in the future, and may require a rework of the firebase data search code

## Chase D.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Chase Dumbacher
Week Ending: |  | 2021-03-17
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Friday | Task(s) performed: | Met with Mike and updated him on progress made on the app including the email and pdf generation successes. Also created new app ipa file and uploaded it to TestFlights to allow Mike to begin testing the app as a whole and providing any feedback. Also looked into calendar pdf generation to try and pinpoint issues
Date: | 2021-03-12 | Result: | Successfully deployed new TestFlights version and notified Mike of it and other progress.
Hours Worked: | 2 | Problems encountered: | calendar issue still requires further debugging.
Day: | Monday | Task(s) performed: | Further troubleshooted and worked on getting the calendar pdf generating and working properly.
Date: | 2021-03-15 | Result: | Fixed the calendar and got the pdfs generating properly and the emails being sent out to the email list and venue email. Fixed issue in the pdf generator where it referenced database data and tried to improperly apply a Util. function to the data to format the text.
Hours Worked: | 2 | Problems encountered: | Debugging the code relating to the documentation functions requires reploying firebase functions each time. Also noticed a navigation bug that was though to be only simulator related but seems to have popped up after dependency updates. (on the slate for tomorrows work)
Day: | Tuesday | Task(s) performed: | Worked on debugging navigation error that was noticed during latest TestFlights build. Looked into any possible differences between VenueViews page pre version 1.06 and post version 1.07
Date: | 2021-03-16 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Wensday | Task(s) performed:
Date: | 2021-03-17 | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Total Hours For The Week |  |  |  | 6

## Sarah P.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Sarah Pham
Week Ending: |  | 2021-03-17
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Thursday | Task(s) performed: | Worked on figuring out the "Send Out Calendar" feature. Tested different levels of architecture to determine where the source of the bug was for the Calendar. The bug ended out not being an issue with the emailing or drive feature that is a part of sending out the Calendar. We narrowed down the issue to be somewhere in the PDF handler because the Calendar feature was the only one that used "events" from the database. So we found even better ways of testing the cloud functions for that feature and were able to see each value the function was pulling from the database by printing it to the cloud functions console. Also updated the code documentation to include all of this trial and error. Found out that the emailer is case sensitive, so thats one reason why an email wasn't sending during the earlier testing phases (also added this to the documentation).
Date: | 2021-03-11 | Result: | There are multiple issues to why the Calendar isn't working and we resolved a few of them. We still need to completely fix the Calendar send out, test Excel exporting, and fix the football events.
Hours Worked: | 2 | Problems encountered: | Calendar was not sending and was returning an internal error. So we commented out the Emailing funtionality and left the Drive to test if the Emailing function was the issue. Long story short, it turns out the Emailing or Drive was not the issue, but rather the PDF builder and the way it handles events. Whenever there was an event on the calendar, the calendar would not know how to export the events correctly and would not send anything except return an internal error. Whenever we removed all events from the Calendar, we would receive an empty campty on our email and the drive.
Day: | Friday | Task(s) performed: | Meeting with Mike, updated him with all results from the past week. He was very happy that we were able to figure out the main issue of the emailing system. He spoke to us about his apple business account and how we might struggle with this whenever we release the latest version to the appstore. Also created a new testflight of the app that included all the working features. Mike has downloaded it and will be testing it this week.
Date: | 2021-03-12 | Result: | Happy meeting. New testflight version.
Hours Worked: | 0.5 | Problems encountered: | We may have issues releasing the official app to the appstore because Mike said he had issues where Apple denied his app because it was not intended for public use but for his personal one. However, he had spoken to Apple and is paying for a Apple business account that we can view and configure on business.apple.com
Day: | Monday | Task(s) performed: | We worked on the Exporting Calendar feature. We figured out the issue was in the way the last group was converting the military time to "normal" central time. It was invalid and we figured this out by making many logs to console and figuring out the error messages. So we successfully got the Calendar feature working. While working on this bug, we found another bug where the edit venues button would go to the wrong page and figured out where the potential issue may lie in the code. Going to work on that tomorrow. We don't see this being a huge issue for Mike though.
Date: | 2021-03-15 | Result: | Calendar feature works! Found a new bug where a button goes to the wrong page, it worked before but now all of sudden it doesn't? We also looked at all commit histories, and found no changes with that feature, which is very mysterious.
Hours Worked: | 2 | Problems encountered: | Editing a venue now leads to the "Create a New Venue" page instead of the editing one.
Day: | Tuesday | Task(s) performed: | Worked on the bug where the "Edit Venue" button leads to the "Create A New Venue" page, researched app stacks, and creation of new testflights.
Date: | 2021-03-16 | Result: | Bug is in the process of getting fixed.
Hours Worked: | 2 | Problems encountered: | Editing a venue now to the "Create a New Venue" page instead of the editing one.
Total Hours For The Week 6.5

## Austin M.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Mongold
Week Ending: |  | 2021-03-17
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed: | Met with Mike
Date: | 2021-03-12 | Result: | Got feedback on current progress
Hours Worked: | 0.5 | Problems encountered: | None
Day: | Saturday | Task(s) performed: | Continued working on the athletic calendars
Date: | 2021-03-13 | Result: | Found some new more promising calendars to try
Hours Worked: | 1.5 | Problems encountered: | Still can't get the imported calendars to show
Day: | Sunday | Task(s) performed:
Date: | 2021-03-14 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed: | Finished getting sports calendars to appear in the website calendar
Date: | 2021-03-15 | Result: | Auburn and Alabama NCAAF schedules are on calendar
Hours Worked: | 3.5 | Problems encountered: | Had to try several different calendar IDs and formats before it appeared, and also had to enable sharing on the specific calendar in use
Day: | Tuesday | Task(s) performed: | Worked on Status Report 2
Date: | 2021-03-16 | Result: | Finished Status Report 2
Hours Worked: | 0.5 | Problems encountered: | None
Day: | Wednesday | Task(s) performed:
Date: | 2021-03-17 | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:

## Austin N.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Newkirk
Week Ending: |  | 2021-03-17
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed: | Setup github and everything on laptop due to extended stay with parents
Date: | 2021-03-12 | Result:
Hours Worked: | 0.5 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2021-03-15 | Result:
Hours Worked: |  | Problems encountered:
Day: | Tuesday | Task(s) performed: | Currently looking into adding firebase data to calendar
Date: | 2021-03-16 | Result:
Hours Worked: | 2 | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
| Total Hours For The Week | 2 |  | Possibly 4?