## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Music Matters Booking System | [6 empty] | Completed | 1
| Team Members: | Chase Dumbacher, Sarah Pham, Austin Mongold, Austin Newkirk | [6 empty] | Discarded | 2
| Date: | 2021-03-27 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To design and create an app and online calendar booking system that is capable of recording and organizing artist names, performance time and dates, and venue names as well as automatically creating and emailing invoices and confirmation documents. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Intents include : Fixing any known bugs in the iOS app, recieving and implementing any feedback from Mike, finalizing all documentation, setting up website document/emailer and venue/client list
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Database To App/Web Sync |  | 2 | 5 | 0 | Completed | 1 | 4
2 | Create Website Framework |  | 1 | 10 | 0 | Completed | 0 | 6
3 | Website Login With FireBase Auth |  | 1 | 3 | 0 | Completed | 0 | 3
4 | Allow Full Cross Platform Usage |  | 3 | 15 | 5 | Collaboration | 1 | 2
5 | Easy To View Calendar |  | 2 | 10 | 10 | Collaboration | 8 | 26
6 | Database Security |  | 3 | 8 | 4 | Collaboration | 0 | 2
7 | App Update And Recovery |  | 3 | 5 | 3 | Collaboration | 0 | 2
8 | Clean User Interface |  | 2 | 15 | 5 | Collaboration | 1 | 1
9 | Football Event Scrapper (Web and iOS) |  | 3 | 30 | 0 | Completed | 0
11 | Functional Web Pdf Builder + Emailer |  | 2 | 15 | 10 | Collaboration | 0
12 | Functional App Pdf Builder + Emailer |  | 1 | 15 | 0 | Completed | 21 | 40
13 | Bug Fix iOS App |  | 2 | 40 | 10 | Collaboration | 8 | 30
14 | Refactoring iOS App |  | 2 | 10 | 5 | Collaboration | 0 | 11
Planned Total |  |  |  | 181 | 52 | Actual Total | 40 | 127

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Music Matters Booking System Team 5
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Chase Dumbacher | 1-4,6,7, 12-14 | 1, 6,7, 12-14 | 1, 6,7, 12-14 | 1-4, 6,7,12-14 | 25 |  |  | 0.5 | 0.5 |  |  | 3.5 | 3.5 | 4 | 4
| Sarah Pham | 6,7, 12-14 | 6,7, 12-14 | 6,7, 12-14 | 6,7,12-14 | 25 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 5 | 5
| Austin Mongold |  | 1,5 | 1,5 |  | 25 | 1 | 1 | 1.5 | 1.5 | 0 | 0 | 2.5 | 2.5 | 5 | 5
| Austin Newkirk |  | 1,5 | 1,5 | 5 | 25 | 0 | 0 | 4 | 4 | 0 | 0 | 7 | 7 | 11 | 11
[5 empty] | Totals | 100 | 1 | 1 | 6.5 | 6.5 | 0 | 0 | 17.5 | 17.5 | 25 | 25
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| App Acomplishments : - Successfully demo'd the app and prooved docuement and email functionality Web Acomplishments : - Got data into json file to work towards solving calendar data problem | [6 empty] | App Objectives: - Functional "Editing" system for venues - Functional Football events showing up on Calendar - Complete and clarified documentation Website Objectives - Have calendar data showing - Begin looking into and setting up firebase functions calls -
| Obstacles encountered since last status report: | [6 empty] | Notes:
| App Team: - Still working on fixing the save function of the edit venue. Web Team: - Event data is still giving trouble being shown on calendar | [6 empty] | - Mike is currently satisfied with current pacing of the project and seems to think we are moving faster/better then preivous groups - Task mangement and tracking has been moved to Monday.com it creates gantt charts based on board tasks and thus helps provide a mangement plan. - The plan should be viewable here https://view.monday.com/1068854366-9fbc2a1db7bba73d7f3618c436ab6452?r=use1 - Team has split into two pairs to help more efficentely work on the two sides of the project (App and Web Teams). Currently the app team is pair programming in effort to better review and bugfix the iOS app. Web team is using a mix of pair programming and scrum like task divying work flow.
Risks facing the project:
App Risk : - None Web Risk : - Calendar data

## Chase D.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Chase Dumbacher
Week Ending: |  | 2021-03-31
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed: | Rescheduled our meeting with Mike and continued looking into the venue edit and save button error. Also setup and filled out team level status report objectives
Date: | 2021-03-26 | Result: | Still continuing working on edit button
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed: | Began updating client data and setting up demo calendar to test replicating the current april month schedule. Communicated with Mike on missing client email data.
Date: | 2021-03-29 | Result: | Filled out calendar with currently up to date clients, awaiting client emails or confirmation from Mike to add new clients and finish calendar for testing
Hours Worked: | 1 | Problems encountered: | Mike didn't include client emails which are part of adding new clients
Day: | Tuesday | Task(s) performed: | Further worked on setting up april calendar for demo/test, also continue working on venue edit and save button error.
Date: | 2021-03-30 | Result:
Hours Worked: | 2 | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Total Hours For The Week |  |  |  | 4

## Sarah P.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Sarah Pham
Week Ending: |  | 2021-03-31
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed: | Presented our presentation to the class. Later updated documentation and worked on fixing the issue with saving while editing a venue.
Date: | 2021-03-26 | Result: | A good presentation and still a few bugs within the app.
Hours Worked: | 3 | Problems encountered: | We found out that the emailing system is case sensitive, which caused a bit of confusion as to why emails weren't getting sent on a certain test. Saving while Editing venues is still bugged. Might have to do with the issue where the component is not mounted, so therefore we cannot have a "memorized state" before processing an update queue. React thinks it's because a component reassigns its own this.props.
Day: | Tuesday | Task(s) performed: | Worked on filling out status report. Also working on a more clarified documentation and hopefully fixing the saving when editing venues bug. As of right now, I am writing this status report it is 12pm and we will not work on this until 3pm today.
Date: | 2021-03-30 | Result: | Hopefully a working edit feature.
Hours Worked: | 2 | Problems encountered: | Editing a venue workings, however saving and deleting does not work whenever we are within that editing view.
Total Hours For The Week 5
Note: I personally did not get to work on the project as much as I usually do, or had hoped due to exams and focusing on other classes. However, this next upcoming week I plan on working more hours.

## Austin M.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Mongold
Week Ending: |  | 2021-03-31
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed: | Started trying to rework code to use a json feed
Date: | 2021-03-26 | Result: | Figured out json format for data and how to add it to calendar events
Hours Worked: | 1.5 | Problems encountered: | Couldn't get it to display yet, but its still early on for this strategy
Day: | Saturday | Task(s) performed:
Date: | 2021-03-27 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2021-03-28 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed: | Continued working on json feed code, got php file set up for loading json feed, learned more on json format, worked on Cycle report
Date: | 2021-03-29 | Result: | Austin Newkirk has data displaying with a flat file, but my laptop won't show anything yet for some reason, finished my cycle report
Hours Worked: | 3.5 | Problems encountered: | Doesn't show data on my laptop for some reason, but works fine on Austin Newkirk's computer using a flat file
Day: | Tuesday | Task(s) performed:
Date: | 2021-03-30 | Result:
Hours Worked: |  | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2021-03-31 | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:

## Austin N.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Newkirk
Week Ending: |  | 2021-03-31
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed: | Discovered that firebase has a .json feature that displays all information as a .json file, which is supported by fullcalendar
Date: | 2021-03-25 | Result: | a way how to solve this problem without adding a new element to our program
Hours Worked: | 2 | Problems encountered: | Fullcalendar implemenation of .json is a bit hard to understand, so planned to figure it out the next day
Day: | Friday | Task(s) performed: | Added a .json file to an example calendar
Date: | 2021-03-26 | Result: | worked perfectly
Hours Worked: | 3 | Problems encountered:
Day: | Friday | Task(s) performed: | Did presentation
Date: | 2021-03-26 | Result:
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed: | Attempted to add the .json file to the actual calendar
Date: | 2021-03-29 | Result: | extremely weird bug?
Hours Worked: | 5 | Problems encountered: | encountered an error that told me that the the .php file the calendar points to needs to be "running." The strangest thing is happening with this bug, however. I did not have this but Friday, and my test calendar worked great with it. FullCalendar even has an example calendar that shows you how to do it. However, EVERY calendar started monday started having this issue. Even the example calendar that FullCalendar comes with? I did a stack overflow to see if I can find the issue.
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Total Hours For The Week