## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Music Matters Booking System | [6 empty] | Completed | 1
| Team Members: | Chase Dumbacher, Sarah Pham, Austin Mongold, Austin Newkirk | [6 empty] | Discarded | 2
| Date: | 2021-03-27 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To design and create an app and online calendar booking system that is capable of recording and organizing artist names, performance time and dates, and venue names as well as automatically creating and emailing invoices and confirmation documents. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Intents include : Fixing any known bugs in the iOS app, recieving and implementing any feedback from Mike, finalizing all documentation, setting up website document/emailer and venue/client list
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Database To App/Web Sync |  | 2 | 5 | 0 | Completed | 2 | 5
2 | Create Website Framework |  | 1 | 10 | 0 | Completed | 0 | 6
3 | Website Login With FireBase Auth |  | 1 | 3 | 0 | Completed | 0 | 3
4 | Allow Full Cross Platform Usage |  | 3 | 15 | 5 | Collaboration | 1 | 2
5 | Easy To View Calendar |  | 2 | 10 | 10 | Collaboration | 21.5 | 37.5
6 | Database Security |  | 3 | 8 | 4 | Completed | 0 | 2
7 | App Update And Recovery |  | 3 | 5 | 3 | Collaboration | 0 | 2
8 | Clean User Interface |  | 2 | 15 | 5 | Collaboration | 1 | 1
9 | Football Event Scrapper (Web and iOS) |  | 3 | 30 | 0 | Completed | 0
11 | Functional Web Pdf Builder + Emailer |  | 2 | 15 | 10 | Adversarial | 0
12 | Functional App Pdf Builder + Emailer |  | 1 | 15 | 0 | Completed | 0 | 19
13 | Bug Fix iOS App |  | 2 | 40 | 10 | Collaboration | 18 | 40
14 | Refactoring iOS App |  | 2 | 10 | 5 | Collaboration | 7.5 | 18.5
Planned Total |  |  |  | 181 | 52 | Actual Total | 51 | 136

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Music Matters Booking System Team 5
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Chase Dumbacher | 1-4,6,7, 12-14 | 1, 6,7, 12-14 | 1, 6,7, 12-14 | 1-4, 6,7,12-14 | 20 | 3 | 3 | 0.5 | 1 | 0.5 | 0.5 | 5.5 | 9 | 9.5 | 13.5
| Sarah Pham | 6,7, 12-14 | 6,7, 12-14 | 6,7, 12-14 | 6,7,12-14 | 20 | 3.5 | 3.5 | 0.5 | 1 | 0 | 0 | 5 | 9.5 | 9 | 14
| Austin Mongold |  | 1,5 | 1,5 |  | 20 | 2 | 3 | 1 | 2.5 | 0.5 | 0.5 | 6 | 8.5 | 9.5 | 14.5
| Austin Newkirk |  | 1,5 | 1,5 | 5 | 20 | 1 | 1 | 2 | 6 | 0 | 0 | 2.5 | 9.5 | 5.5 | 16.5
[5 empty] | Totals | 80 | 9.5 | 10.5 | 4 | 10.5 | 1 | 1 | 19 | 36.5 | 33.5 | 58.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| App Acomplishments : - Successfully fixed venue edit button without causing any new problems - Reproduced april calendar compared to Mikes Web Acomplishments : - Started testing with json data - Found how to view json data from firebase | [6 empty] | App Objectives: - Full finished dev story/documentation. - Start on user manuals and hand off documentation. - Final update push to testflights and app store builds. - Continue looking into app store release if not done. Website Objectives - - Try to get some json display from firebase on the website - Start cleaning up code for later documentation
| Obstacles encountered since last status report: | [6 empty] | Notes:
| App Team: - App store release Web Team: - The json format used by firebase and fullcalendar are different from each other | [6 empty] | - Mike is currently satisfied with current pacing of the project and seems to think we are moving faster/better then preivous groups - Task mangement and tracking has been moved to Monday.com it creates gantt charts based on board tasks and thus helps provide a mangement plan. - The plan should be viewable here https://view.monday.com/1068854366-9fbc2a1db7bba73d7f3618c436ab6452?r=use1 - Team has split into two pairs to help more efficentely work on the two sides of the project (App and Web Teams). Currently the app team is pair programming in effort to better review and bugfix the iOS app. Web team is using a mix of pair programming and scrum like task divying work flow.
Risks facing the project:
App Risk : - None Web Risk : - Calendar data

## Chase D.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Chase Dumbacher
Week Ending: |  | 2021-04-07
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Wenesday | Task(s) performed: | Attempted to fix the edit venue button. Tried setting up the pages to call the class within the same file by renaming and redirecting it.
Date: | 2021-03-31 | Result: | Still Working on this issue, plan to use previous versions and step through previous changes to find the cause
Hours Worked: | 2.5 | Problems encountered: | Issues renaming view classes due to app stack navigation.
Day: | Thursday | Task(s) performed: | Continued working on edit venue button fix. Used git version control to pull previous working version of the code and worked through making previous changes and checking for edit venue button error. Uploaded new test flight of new and working version. Updated documentation. Updated app store pending version info
Date: | 2021-04-01 | Result: | Successfully got edit venue button working with all previous functionalities.
Hours Worked: | 2 | Problems encountered:
Day: | Saturday |  | Met with Mike and part of the team to discuss progress for the week and demonstrate current capabilities of the app. Discussed with Mike current delays and plans for the end of the semester
Date: | 2021-04-03 |  | successful meeting
Hours Worked: | 0.5
Day: | Monday | Task(s) performed: | Began refactoring the app in specific the document functions and email send out. Also added new clients to client list to test and compare full april calendar with Mike's hand down calendar pdf. Also worked on filling out the status sheet as well as informing everyone of needed work.
Date: | 2021-04-05 | Result: | successfully condensed the confirmation and invoice functions into one similar function. also added all new clients and reproduced april calendar
Hours Worked: | 2.5 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Continued trying to refactor the app this time in renaming (while keep current functionality in tact) the different pages and associated classes to be more understandable. Also looked into accessing the app on the app store.
Date: | 2021-04-06 | Result:
Hours Worked: | 2 | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Total Hours For The Week |  |  |  | 9.5

## Sarah P.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Sarah Pham
Week Ending: |  | 2021-04-07
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Wednesday | Task(s) performed: | Worked on the "Edit Venue" functionality. Practically tried everything we could think of. We thought it was the issue of redundant code, but then we pulled the old git and commented out the redundant code and it still worked. Updated documentation and status report.
Date: | 2021-03-31 | Result: | Edit venue still does not work. Very frustating since we never touched anything with the feature.
Hours Worked: | 2.5 | Problems encountered: | Everything we try and research does not work.
Day: | Thursday | Task(s) performed: | Pulled previous working version and worked incrementally through previous git logs. Uploaded new testflight. Updated documentation. Created plans for tomorrow and rest of cycle. Worked on status report. We also noticed that the appstore account is expiring April 19 of this month, so we will need to speak to Mike about this. Updated the next pending app releasal information, such as the sign in, the copyright, the version information.
Date: | 2021-04-01 | Result: | A new uploaded testflight with a working venue edit feature!
Hours Worked: | 2 | Problems encountered: | None
Day: | Monday | Task(s) performed: | Refactored much of the code that really bothered us while we were working on the project. The emailing system had a separate function for each type of document generated (Confirmation, Invoice, Booking List, and Calendar). So we refactored it into one function. Updated much of the documentation, included information on the appstore versions and build numbers. Redeployed cloud functions after every change and tested incrementally to avoid causing any future errors. Updated and cleaned up file structure, committed and pushed everything to a separate branch on Git.
Date: | 2021-04-05 | Result: | Refactored the emailing system, there is still more refactoring needed to be done. We also need to change the names of the files, lots of code smells. Updated documentation.
Hours Worked: | 2.5 | Problems encountered: | None
Day: | Tuesday | Task(s) performed: | Renamed some horrible functions, tested incrementally, and redeployed cloud functions. Updated documentation. Created new testflight.
Date: | 2021-04-06 | Result: | New testflight and refactored code.
Hours Worked: | 2 | Problems encountered: | None
Total Hours For The Week 9

## Austin M.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Mongold
Week Ending: |  | 2021-04-07
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Wednesday | Task(s) performed: | Looked into alternatives to using firebase to create an array. Started learning about json use in fullcalendar
Date: | 2021-03-31 | Result:
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2021-04-01 | Result:
Hours Worked: |  | Problems encountered:
Day: | Friday | Task(s) performed: | Started working on json data for calendar instead of firebase array creation
Date: | 2021-04-02 | Result: | Got the firebase json to show and had some success in testing a .json
Hours Worked: | 4 | Problems encountered: | Firebase and fullcalendar use a different format for json files
Day: | Saturday | Task(s) performed: | Met with Mike to discuss progress
Date: | 2021-04-03 | Result: | He said he is happy the website is coming along, but we may have to go to another team to finish it since we have been stuck
Hours Worked: | 0.5 | Problems encountered: | None
Day: | Sunday | Task(s) performed:
Date: | 2021-04-04 | Result:
Hours Worked: |  | Problems encountered:
Day: | Monday | Task(s) performed: | Started creating tests to see how a json file works and how html, javascript, and fullcalendar handle it
Date: | 2021-04-05 | Result: | Got several in-code examples to work and learned about their functionality
Hours Worked: | 3 | Problems encountered: | Couldn't get any url or file jsons to work
Day: | Tuesday | Task(s) performed: | Worked on updating status report
Date: | 2021-04-06 | Result: | Finished status report
Hours Worked: | 1 | Problems encountered: | None
Day: |  | Task(s) performed:
Date: | 2021-04-07 | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
9.5

## Austin N.
COMP4710 Status Report - Member Timesheet
Project Name: |  | Music Matters Booking System
Member: |  | Austin Newkirk
Week Ending: |  | 2021-04-07
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Monday | Task(s) performed: | Figured out how to display a JSON file onto the calendar
Date: | 2021-03-29 | Result: | Figured out how to display a correctly formatted JSON file onto the calendar
Hours Worked: | 3 | Problems encountered: | None, but firebase formats there json slightly differently, need to figure out how to change the format
Day: | Thursday | Task(s) performed: | Looked more into the PHP problem for possible reformatting
Date: | 2021-04-01 | Result: | the PHP bug still is there, and I do not know why
Hours Worked: | 2 | Problems encountered: | PHP bug still there
Day: | Friday | Task(s) performed: | Asked a question on stack overflow to see if I can get help
Date: | 2021-04-02 | Result: | Some useful stuff, but ultimately nothing
Hours Worked: | 0.5 | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered: | Have a big exam tomorrow, so started focusing on that. Did some overtime last week to equalize hours
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
| Total Hours For The Week |  | 5.5